## Sheet1
|  | Project Name: | Inventory Management System
|  | Project Description: | Creating and deploying an inventory management system
|  | Project Owner: | Matt Garbett
Risk ID | Date registered | Risk | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 2021-01-14 | Covid-19 | Pandemic |  |  | x |  | x |  | Flu like symptoms | 2 weeks | Let the trainers know and work when possible/after recovery
2 | 2021-01-14 | Internet connection | Internet connection dropping or broadband speeds slow | x |  |  |  | x |  | Unable to work on project or perform the presentaion and slow loading times | Hours | Reset router Contact broadband company
3 | 2021-01-14 | Distractions | Disractions on PC or around the room/house |  | x |  |  |  | x | Slow down progress on the project which could rush things and make mistakes | Hours | Work during work times and have enough breaks Remove distractions from workspace
4 | 2021-01-14 | Tiredness | Early morning and late afternoon being tired |  | x |  |  | x |  | Make mistakes on project and slow progress of project | 30 minutes | Don't stay up too late Get up early to do recap/ extra work
5 | 2021-01-14 | Headaches | Staring at the screen for too long | x |  |  | x |  |  | Project progress could be hindered | 30 minutes | Take breaks from looking at the screen even during breaks
6 | 2021-01-14 | Lack of Understanding | Part of project may have things I do not know |  | x |  |  |  | x | Project progress slowed | Hours | Research the parts of the project I do not understand and recap on QA community
7 | 2021-01-14 | PC breaks | PC could suffer software or hardware damage | x |  |  |  |  | x | Project severily hindered | Days | Ask for extension and a replacement laptop to be sent
8 | 2021-01-14 | Injury | Injury at home | x |  |  |  | x |  | Project could be postponed if injury is bad/severe | Days | Recover from injury or if injury not too bad carry on but let trainers know
9 | 2021-01-14 | Accidental Deletions | Deleting files or messing up git | x |  |  |  |  | x | Could potentially cause many complications for project | Days | Return to previous git commit or recover files deleted and restore progress
10 | 2021-01-14 | Not meeting minimum requirements | Could miss out important parts of project spec | x |  |  |  |  | x | Final Project may seem done but missing parts | Hours | Make sure to read specification for project carefully and have met criteria